## project-content-template (1)
phase | operation | step | step_description | inputs | output_name | output_description | output_type | tool_name | tool_description | material_name | material_description
Prep | Project Setup | Furniture and belongings move | Remove furniture, fixtures, and personal items; protect adjacent surfaces | * Furniture qty * Distance to project | No personal areas affected by dust
Prep | Project Setup | Heavy appliance move | Remove large appliances such as refrigerators | * Furniture qty * Distance to project | No personal areas affected by dust
Prep | Project Setup | Work station setup | Position mixing tools, water supply, cutting tools, and waste bins within easy reach while keeping the main floor clear. | * Distance to project | No personal areas affected by dust
Prep | Project Setup | Work station setup | Position mixing tools, water supply, cutting tools, and waste bins within easy reach while keeping the main floor clear. | * Distance to project | Driveway / hard surfaces protected from dust
Prep | Project Setup | Work station setup | Position mixing tools, water supply, cutting tools, and waste bins within easy reach while keeping the main floor clear. | * Distance to project | Setup: Workbench, mixing area with water supply, cutting table, re-useable scraps, and final waste tile.
Prep | Project Setup | Materials staging | Lay out tile boxes in installation order; pre-open shrink wrap to acclimate tiles to room temperature and humidity. | * Duration check method | No personal areas affected by dust
Prep | Project Setup | Materials staging | Lay out tile boxes in installation order; pre-open shrink wrap to acclimate tiles to room temperature and humidity. | * Duration check method | Acclimation time passed mfg minimum
Prep | Hazardous materials removal | Remove hazardous materials | If old adhesives or flooring contain asbestos or lead, hire a certified abatement contractor and follow containment protocols. | * Compliance reqts * Hazardous material type | Hazardous materials remove and disposed of in compliance with federal, state, and local building codes
Prep | Demo | Remove non-hazardous materials | Strip carpet, vinyl, or existing tile down to the substrate; use scrapers and floor scrubbing tools to clear residue. | * Flooring materials volume * Material type * Nail volume | Old materials removed from floor
Prep | Demo | Remove tile (>100sqft) | Strip tile using machine | * Flooring materials volume * Material type * Nail volume | Tile removed from floor
Prep | Demo | Remove wall trim and prepare walls | Remove trim and loose materials from walls | * Stud location marking * Caulk cutting/paint scoring * Nail volume | Old materials removed from wall
Prep | Demo | Remove wall trim and prepare walls | Remove trim and loose materials from walls | * Stud location marking * Caulk cutting/paint scoring * Nail volume | No paint tears
Prep | Demo | Remove wall trim and prepare walls | Remove trim and loose materials from walls | * Stud location marking * Caulk cutting/paint scoring * Nail volume | No dents to drywall above baseboard
Prep | Demo | Remove wall trim and prepare walls | Remove trim and loose materials from walls | * Stud location marking * Caulk cutting/paint scoring * Nail volume | No cracking to baseboard materials
Prep | Demo | Remove toilet | Remove toilet from bathroom floor |  | Toilet removed
Prep | Demo | Remove toilet | Remove toilet from bathroom floor | *Toilet type/install method *Bolt rust *Lifting method *Water level *Water valve control | Wax residue removed
Prep | Demo | Remove toilet | Remove toilet from bathroom floor | *Toilet type/install method *Bolt rust *Lifting method *Water level *Water valve control | Flange condition inspected and documented
Prep | Demo | Remove toilet | Remove toilet from bathroom floor | *Toilet type/install method *Bolt rust *Lifting method *Water level *Water valve control | Toilet drain pipe plugged
Prep | Demo | Remove toilet | Remove toilet from bathroom floor | *Toilet type/install method *Bolt rust *Lifting method *Water level *Water valve control | No water spilled in house
Prep | Demo - wood floor | Detailed finishing and prep | Fill cracks or low spots with patching compound; sand protrusions to achieve a uniform, flat surface. | * Surface inspection method | Nails removed
Prep | Demo - wood floor | Detailed finishing and prep | Fill cracks or low spots with patching compound; sand protrusions to achieve a uniform, flat surface. | * Surface inspection method | No loose debris / contamination
Prep | Demo - wood floor | Detailed finishing and prep | Fill cracks or low spots with patching compound; sand protrusions to achieve a uniform, flat surface. | * Surface inspection method | Loose boards screwed down
Prep | Subfloor prep | Prep concrete | If concrete surface is not smooth, grind concrete slabs to remove laitance and improve thinset adhesion. | *Grinding method *High point marking *High point identification method *Verification method | Concrete surface roughness prepared for thinset - 100% coverage
Prep | Subfloor prep | Prep concrete | If concrete surface is not smooth, grind concrete slabs to remove laitance and improve thinset adhesion. | *Grinding method *High point marking *High point identification method *Verification method | No high points >1/8" in 10ft for natural stone, 1/4" in 10ft for ceramic/porcelain
Prep | Assess floor | Measure | Re-verify dimensions after demo to account for any substrate changes; adjust layout plans as needed. Check moisture using moisture meter. | * Inspection method * | Condition report:
Prep | Assess floor | Measure | Re-verify dimensions after demo to account for any substrate changes; adjust layout plans as needed. Check moisture using moisture meter. | * Inspection method * | Moisture level
Prep | Assess floor | Measure | Re-verify dimensions after demo to account for any substrate changes; adjust layout plans as needed. Check moisture using moisture meter. | * Inspection method * | Level
Prep | Assess floor | Measure | Re-verify dimensions after demo to account for any substrate changes; adjust layout plans as needed. Check moisture using moisture meter. | * Inspection method * | Subfloor thickness
Prep | Assess floor | Measure | Re-verify dimensions after demo to account for any substrate changes; adjust layout plans as needed. Check moisture using moisture meter. | * Inspection method * | Subfloor material
Prep | Assess floor | Measure | Re-verify dimensions after demo to account for any substrate changes; adjust layout plans as needed. Check moisture using moisture meter. | * Inspection method * | Transition zones
Prep | Assess floor | Measure | Re-verify dimensions after demo to account for any substrate changes; adjust layout plans as needed. Check moisture using moisture meter. | * Inspection method * | Moulding heights
Prep | Subfloor prep | Install plywood subfloor | If subfloor thickness is <1-1/4" Screw down exterior-grade plywood over joists to create a stiff, screw-retention layer under tile. | * Adhevsive coverage and thickness * Screwing pattern | Subfloor total thickness >1-1/4", no layer <3/8"
Prep | Subfloor prep | Install plywood subfloor | If subfloor thickness is <1-1/4" Screw down exterior-grade plywood over joists to create a stiff, screw-retention layer under tile. | * Adhevsive coverage and thickness * Screwing pattern | Screws at least every 6"; no closer than 1/2" from edge
Prep | Subfloor prep | Install plywood subfloor | If subfloor thickness is <1-1/4" Screw down exterior-grade plywood over joists to create a stiff, screw-retention layer under tile. | * Adhevsive coverage and thickness * Screwing pattern | Screws at least every 6"; no closer than 1/2" from edge
Prep | Subfloor prep | Install plywood subfloor | If subfloor thickness is <1-1/4" Screw down exterior-grade plywood over joists to create a stiff, screw-retention layer under tile. | * Adhevsive coverage and thickness * Screwing pattern | Construction adhesive 95% applied to joists / underlying base
Prep | Subfloor prep | Apply self-leveler | If subfloor flatness is not 1/8" in 10ft or not level, Pour and spread self-leveling compound to smooth minor dips | * Surface cleanliness * Primer application * Mix consitnecy * Application time since mix * Mfg of self-leveler * Spread method * Gauge rake setting | Smooth - 1/8" in 10ft
Prep | Subfloor prep | Apply self-leveler | If subfloor flatness is not 1/8" in 10ft or not level, Pour and spread self-leveling compound to smooth minor dips | * Surface cleanliness * Primer application * Mix consitnecy * Application time since mix * Mfg of self-leveler * Spread method * Gauge rake setting | Adhesion of layer in mfg spec
Prep | Subfloor prep | Apply self-leveler | If subfloor flatness is not 1/8" in 10ft or not level, Pour and spread self-leveling compound to smooth minor dips | * Surface cleanliness * Primer application * Mix consitnecy * Application time since mix * Mfg of self-leveler * Spread method * Gauge rake setting | No drips to lower levels/outside project floor
Prep | Subfloor prep | Apply self-leveler | If subfloor flatness is not 1/8" in 10ft or not level, Pour and spread self-leveling compound to smooth minor dips | * Surface cleanliness * Primer application * Mix consitnecy * Application time since mix * Mfg of self-leveler * Spread method * Gauge rake setting | Max thickness per mfg spec
Prep | Cleaning | Clean tools | Remove thinset from tools | * Thinset waste location; water rinse duration * Thinset removal accuracy | Thinset completely removed from tools
Prep | Cleaning | Clean tools | Remove thinset from tools | * Thinset waste location; water rinse duration * Thinset removal accuracy | Thinset not settling in drains
Prep | Subfloor prep | Cure self leveler | Allow leveler cure time before proceeding. | * Manufacturer specification * Time track method | Wait time passed in line with manufacturer recommendation
Prep | Tile base install | Install concrete board | If using concrete board, Fasten cement board panels with corrosion-resistant screws; tape seams with fiber mesh to prevent movement cracks. | * Thinset coverage * Trowel size * Screw pattern * Layout plan | Screws every 6", not closer than 1" from edge
Prep | Tile base install | Install concrete board | If using concrete board, Fasten cement board panels with corrosion-resistant screws; tape seams with fiber mesh to prevent movement cracks. | * Thinset coverage * Trowel size * Screw pattern * Layout plan | Screws every 6", not closer than 1" from edge
Prep | Tile base install | Install concrete board | If using concrete board, Fasten cement board panels with corrosion-resistant screws; tape seams with fiber mesh to prevent movement cracks. | * Thinset coverage * Trowel size * Screw pattern * Layout plan | Thinset coverage and strength
Prep | Tile base install | Install concrete board | If using concrete board, Fasten cement board panels with corrosion-resistant screws; tape seams with fiber mesh to prevent movement cracks. | * Thinset coverage * Trowel size * Screw pattern * Layout plan | Thinset coverage and strength
Prep | Tile base install | Install concrete board | If using concrete board, Fasten cement board panels with corrosion-resistant screws; tape seams with fiber mesh to prevent movement cracks. | * Thinset coverage * Trowel size * Screw pattern * Layout plan | Seam staggering
Prep | Tile base install | Install concrete board | If using concrete board, Fasten cement board panels with corrosion-resistant screws; tape seams with fiber mesh to prevent movement cracks. | * Thinset coverage * Trowel size * Screw pattern * Layout plan | Seam 100% coverage with tape
Prep | Tile base install | Install concrete board | If using concrete board, Fasten cement board panels with corrosion-resistant screws; tape seams with fiber mesh to prevent movement cracks. | * Thinset coverage * Trowel size * Screw pattern * Layout plan | Floor gaps 1/4"-1/2"
Prep | Tile base install | Install concrete board | If using concrete board, Fasten cement board panels with corrosion-resistant screws; tape seams with fiber mesh to prevent movement cracks. | * Thinset coverage * Trowel size * Screw pattern * Layout plan | Floor gaps 1/4"-1/2"
Prep | Tile base install | Install uncoupling membrane | If using uncoupling membrane, Roll out and bond a membrane to isolate tile from substrate stresses and manage moisture. | * Trowel size * Trowel angle * Towel direction * Setting pressure * Setting force direction * Layout plan * Thinset type | Thinset coverage and strength
Prep | Tile base install | Install uncoupling membrane | If using uncoupling membrane, Roll out and bond a membrane to isolate tile from substrate stresses and manage moisture. | * Trowel size * Trowel angle * Towel direction * Setting pressure * Setting force direction * Layout plan * Thinset type | Thinset coverage and strength
Prep | Tile base install | Install uncoupling membrane | If using uncoupling membrane, Roll out and bond a membrane to isolate tile from substrate stresses and manage moisture. | * Trowel size * Trowel angle * Towel direction * Setting pressure * Setting force direction * Layout plan * Thinset type | Seam 100% coverage with tape
Prep | Tile base install | Install uncoupling membrane | If using uncoupling membrane, Roll out and bond a membrane to isolate tile from substrate stresses and manage moisture. | * Trowel size * Trowel angle * Towel direction * Setting pressure * Setting force direction * Layout plan * Thinset type | Floor gaps 1/4"-1/2"
Prep | Tile base install | Install uncoupling membrane | If using uncoupling membrane, Roll out and bond a membrane to isolate tile from substrate stresses and manage moisture. | * Trowel size * Trowel angle * Towel direction * Setting pressure * Setting force direction * Layout plan * Thinset type | Floor gaps 1/4"-1/2"
Prep | Cleaning | Clean tools | Remove thinset from tools | * Thinset waste location; water rinse duration * Thinset removal accuracy | Thinset completely removed from tools
Prep | Layout | Plan layout | Plan layout using digital tools | * Accurate measurements w/ grout * Reference walls | reference walls defined
Prep | Layout | Plan layout | Plan layout using digital tools | * Accurate measurements w/ grout * Reference walls | starting line defined
Prep | Layout | Plan layout | Plan layout using digital tools | * Accurate measurements w/ grout * Reference walls | min 2" or 1/3 width on all tiles
Prep | Layout | Plan layout | Plan layout using digital tools | * Accurate measurements w/ grout * Reference walls | balanced spacing
Prep | Layout | Plan layout | Plan layout using digital tools | * Accurate measurements w/ grout * Reference walls | setting order defined (planning for no-walk on tile)
Prep | Layout | Plan layout | Plan layout using digital tools | * Accurate measurements w/ grout * Reference walls | grout line per design; min 1/16"
Prep | Layout | Plan layout | Plan layout using digital tools | * Accurate measurements w/ grout * Reference walls | Movement joint every 25ft
Prep | Layout | Dry test layout | Test layout for critical zones | * Layout plan * Tile handling method | Layout plan
Prep | Layout | Dry test layout | Test layout for critical zones | * Layout plan * Tile handling method | No broken tiles
Install | Cut | Wet saw cut | Use a water-cooled tile saw for straight, precise cuts on ceramic, porcelain, or natural stone. | * Saw blade condition * Feed rate * Water flow * Cut location along marking line (+/- 1/16") * Guide fence * Layout: high-stress cuts * Plunge cuts and drilling | Cut according to size - +/-1/16"
Install | Cut | Wet saw cut | Use a water-cooled tile saw for straight, precise cuts on ceramic, porcelain, or natural stone. | * Saw blade condition * Feed rate * Water flow * Cut location along marking line (+/- 1/16") * Guide fence * Layout: high-stress cuts * Plunge cuts and drilling | Round cut according to profile - +/-1/4"
Install | Cut | Wet saw cut | Use a water-cooled tile saw for straight, precise cuts on ceramic, porcelain, or natural stone. | * Saw blade condition * Feed rate * Water flow * Cut location along marking line (+/- 1/16") * Guide fence * Layout: high-stress cuts * Plunge cuts and drilling | No cracking of tile in-plane
Install | Cut | Snap & score cut | For thinner tiles, use a handheld snap cutter: score the glaze, snap the tile along the line, and smooth edges with a rubbing stone. | * Marking layout - using wax pencil or sharpie * Roller wheel condition * Score pressure * Snap pressure * Cut location along marking line (+/- 1/16") * Guide fence | Straight cut according to size - +/-1/16"
Install | Cut | Snap & score cut | For thinner tiles, use a handheld snap cutter: score the glaze, snap the tile along the line, and smooth edges with a rubbing stone. | * Marking layout - using wax pencil or sharpie * Roller wheel condition * Score pressure * Snap pressure * Cut location along marking line (+/- 1/16") * Guide fence | No cracking of tile in-plane
Install | Cut | Grinder cut | Use an angle grinder with a diamond blade for curved or notched cuts | * Saw blade condition * Feed rate * Water flow * Cut location along marking line (+/- 1/16") * Wheel speed * Wheel feed | Round cut according to size - +/-1/4"
Install | Cut | Grinder cut | Use an angle grinder with a diamond blade for curved or notched cuts | * Saw blade condition * Feed rate * Water flow * Cut location along marking line (+/- 1/16") * Wheel speed * Wheel feed | Straight cut according to size - +/-1/8"
Install | Cut | Grinder cut | Use an angle grinder with a diamond blade for curved or notched cuts | * Saw blade condition * Feed rate * Water flow * Cut location along marking line (+/- 1/16") * Wheel speed * Wheel feed | No cracking of tile in-plane
Install | Cut | Cut trim | For metal edge profiles, cut to size | * Marking layout * Cut location along marking line (+/- 1/16") | Cut within +/-1/32"
Install | Cut | Drill | Fit tiles to pipes or other fixtures by drilling pilot holes first, then widen with a diamond-tipped bit under water spray. | * Drill condition * Water flow * Drill pressure * Drill guide * Starting method * Drill spin speed | No cracking of tile in-plane
Install | Cut | Drill | Fit tiles to pipes or other fixtures by drilling pilot holes first, then widen with a diamond-tipped bit under water spray. | * Drill condition * Water flow * Drill pressure * Drill guide * Starting method * Drill spin speed | Hole diameter outside of 1/4" from plan
Install | Cut | Drill | Fit tiles to pipes or other fixtures by drilling pilot holes first, then widen with a diamond-tipped bit under water spray. | * Drill condition * Water flow * Drill pressure * Drill guide * Starting method * Drill spin speed | Hole true position within 1/8"
Install | Cut | Polish | Smooth cut edges and chamfers with a fine-grit diamond grinder or hand scraper for a professional finish. | * UPSTREAM: Cut speed * UPSTREAM: Water flow * Polishing grit * Polishing speed * Polishing pressure * Polishing location | No cracking of tile in-plane
Install | Cut | Polish | Smooth cut edges and chamfers with a fine-grit diamond grinder or hand scraper for a professional finish. | * UPSTREAM: Cut speed * UPSTREAM: Water flow * Polishing grit * Polishing speed * Polishing pressure * Polishing location | No visible chips on edge (no magnification, 4" distance)
Install | Cut | Polish | Smooth cut edges and chamfers with a fine-grit diamond grinder or hand scraper for a professional finish. | * UPSTREAM: Cut speed * UPSTREAM: Water flow * Polishing grit * Polishing speed * Polishing pressure * Polishing location | Inner corner radius maintained per layout
Install | Cut | Polish | Smooth cut edges and chamfers with a fine-grit diamond grinder or hand scraper for a professional finish. | * UPSTREAM: Cut speed * UPSTREAM: Water flow * Polishing grit * Polishing speed * Polishing pressure * Polishing location | <1/64" matl removal
Install | Mix | Mix thinset | Combine mortar and water to a lump-free, peanut-butter consistency; slake (rest) then remix before use. | * Water and thinset volume per mfg spec * Mix time (Min 5min) * Mix speed * Paddle type | Peanut-butter consistency and no unmixed contents
Install | Mix | Mix thinset | Combine mortar and water to a lump-free, peanut-butter consistency; slake (rest) then remix before use. | * Water and thinset volume per mfg spec * Mix time (Min 5min) * Mix speed * Paddle type | Peanut-butter consistency and no unmixed contents
Install | Mix | Mix thinset | Combine mortar and water to a lump-free, peanut-butter consistency; slake (rest) then remix before use. | * Water and thinset volume per mfg spec * Mix time (Min 5min) * Mix speed * Paddle type | Peanut-butter consistency and no unmixed contents
Install | Mix | Mix thinset | Combine mortar and water to a lump-free, peanut-butter consistency; slake (rest) then remix before use. | * Water and thinset volume per mfg spec * Mix time (Min 5min) * Mix speed * Paddle type | End time of mix logged
Install | Set | Clean floor | Clean floor |  | No contamination
Install | Set | Apply thinset | Spread mortar with a notched trowel at the correct angle and depth to achieve complete coverage and target bed thickness. | * Time since mix completion * Trowel notch size * Trowel coverage * Handlnig method * Hard points near tile | 95% thinset coverage
Install | Set | Apply thinset | Spread mortar with a notched trowel at the correct angle and depth to achieve complete coverage and target bed thickness. | * Time since mix completion * Trowel notch size * Trowel coverage * Handlnig method * Hard points near tile | Thinset thickness <1/8"
Install | Set | Apply thinset | Spread mortar with a notched trowel at the correct angle and depth to achieve complete coverage and target bed thickness. | * Time since mix completion * Trowel notch size * Trowel coverage * Handlnig method * Hard points near tile | Tiles undamaged
Install | Set | Set tile | Press and wiggle each tile into the mortar bed, maintaining consistent spacing with wedges or spacers and periodic level checks. | * UPSTREAM: Floor flatness * UPSTREAM: Layout pattern * UPSTREAM: Grout size * UPSTREAM: Tile flatness * Thinset volume * Thinset consistency * Thinset troweling * Thinset time since mix * Leveling system pressure * Location of leveling spacers * Tile setting pressure too low * Tile setting wiggle too little * Floor contamination | Lippage <1/32"
Install | Set | Set tile | Press and wiggle each tile into the mortar bed, maintaining consistent spacing with wedges or spacers and periodic level checks. | * UPSTREAM: Floor flatness * UPSTREAM: Layout pattern * UPSTREAM: Grout size * UPSTREAM: Tile flatness * Thinset volume * Thinset consistency * Thinset troweling * Thinset time since mix * Leveling system pressure * Location of leveling spacers * Tile setting pressure too low * Tile setting wiggle too little * Floor contamination | Lippage <1/32"
Install | Set | Set tile | Press and wiggle each tile into the mortar bed, maintaining consistent spacing with wedges or spacers and periodic level checks. | * UPSTREAM: Floor flatness * UPSTREAM: Layout pattern * UPSTREAM: Grout size * UPSTREAM: Tile flatness * Thinset volume * Thinset consistency * Thinset troweling * Thinset time since mix * Leveling system pressure * Location of leveling spacers * Tile setting pressure too low * Tile setting wiggle too little * Floor contamination | Lippage <1/32"
Install | Set | Set tile | Press and wiggle each tile into the mortar bed, maintaining consistent spacing with wedges or spacers and periodic level checks. | * UPSTREAM: Floor flatness * UPSTREAM: Layout pattern * UPSTREAM: Grout size * UPSTREAM: Tile flatness * Thinset volume * Thinset consistency * Thinset troweling * Thinset time since mix * Leveling system pressure * Location of leveling spacers * Tile setting pressure too low * Tile setting wiggle too little * Floor contamination | Lippage <1/32"
Install | Set | Set tile | Press and wiggle each tile into the mortar bed, maintaining consistent spacing with wedges or spacers and periodic level checks. | * UPSTREAM: Floor flatness * UPSTREAM: Layout pattern * UPSTREAM: Grout size * UPSTREAM: Tile flatness * Thinset volume * Thinset consistency * Thinset troweling * Thinset time since mix * Leveling system pressure * Location of leveling spacers * Tile setting pressure too low * Tile setting wiggle too little * Floor contamination | Lippage <1/32"
Install | Set | Set tile | Press and wiggle each tile into the mortar bed, maintaining consistent spacing with wedges or spacers and periodic level checks. | * UPSTREAM: Floor flatness * UPSTREAM: Layout pattern * UPSTREAM: Grout size * UPSTREAM: Tile flatness * Thinset volume * Thinset consistency * Thinset troweling * Thinset time since mix * Leveling system pressure * Location of leveling spacers * Tile setting pressure too low * Tile setting wiggle too little * Floor contamination | Lippage <1/32"
Install | Set | Set tile | Press and wiggle each tile into the mortar bed, maintaining consistent spacing with wedges or spacers and periodic level checks. | * UPSTREAM: Floor flatness * UPSTREAM: Layout pattern * UPSTREAM: Grout size * UPSTREAM: Tile flatness * Thinset volume * Thinset consistency * Thinset troweling * Thinset time since mix * Leveling system pressure * Location of leveling spacers * Tile setting pressure too low * Tile setting wiggle too little * Floor contamination | Lippage <1/32"
Install | Set | Set tile | Press and wiggle each tile into the mortar bed, maintaining consistent spacing with wedges or spacers and periodic level checks. | * UPSTREAM: Floor flatness * UPSTREAM: Layout pattern * UPSTREAM: Grout size * UPSTREAM: Tile flatness * Thinset volume * Thinset consistency * Thinset troweling * Thinset time since mix * Leveling system pressure * Location of leveling spacers * Tile setting pressure too low * Tile setting wiggle too little * Floor contamination | Lippage <1/32"
Install | Set | Set tile | Press and wiggle each tile into the mortar bed, maintaining consistent spacing with wedges or spacers and periodic level checks. | * UPSTREAM: Floor flatness * UPSTREAM: Layout pattern * UPSTREAM: Grout size * UPSTREAM: Tile flatness * Thinset volume * Thinset consistency * Thinset troweling * Thinset time since mix * Leveling system pressure * Location of leveling spacers * Tile setting pressure too low * Tile setting wiggle too little * Floor contamination | Lippage <1/32"
Install | Set | Set tile | Press and wiggle each tile into the mortar bed, maintaining consistent spacing with wedges or spacers and periodic level checks. | * UPSTREAM: Floor flatness * UPSTREAM: Layout pattern * UPSTREAM: Grout size * UPSTREAM: Tile flatness * Thinset volume * Thinset consistency * Thinset troweling * Thinset time since mix * Leveling system pressure * Location of leveling spacers * Tile setting pressure too low * Tile setting wiggle too little * Floor contamination | Lippage <1/32"
Install | Set | Set tile | Press and wiggle each tile into the mortar bed, maintaining consistent spacing with wedges or spacers and periodic level checks. | * UPSTREAM: Floor flatness * UPSTREAM: Layout pattern * UPSTREAM: Grout size * UPSTREAM: Tile flatness * Thinset volume * Thinset consistency * Thinset troweling * Thinset time since mix * Leveling system pressure * Location of leveling spacers * Tile setting pressure too low * Tile setting wiggle too little * Floor contamination | Lippage <1/32"
Install | Set | Set tile | Press and wiggle each tile into the mortar bed, maintaining consistent spacing with wedges or spacers and periodic level checks. | * UPSTREAM: Floor flatness * UPSTREAM: Layout pattern * UPSTREAM: Grout size * UPSTREAM: Tile flatness * Thinset volume * Thinset consistency * Thinset troweling * Thinset time since mix * Leveling system pressure * Location of leveling spacers * Tile setting pressure too low * Tile setting wiggle too little * Floor contamination | Lippage <1/32"
Install | Set | Set tile | Press and wiggle each tile into the mortar bed, maintaining consistent spacing with wedges or spacers and periodic level checks. | * UPSTREAM: Floor flatness * UPSTREAM: Layout pattern * UPSTREAM: Grout size * UPSTREAM: Tile flatness * Thinset volume * Thinset consistency * Thinset troweling * Thinset time since mix * Leveling system pressure * Location of leveling spacers * Tile setting pressure too low * Tile setting wiggle too little * Floor contamination | Lippage <1/32"
Install | Set | Set tile | Press and wiggle each tile into the mortar bed, maintaining consistent spacing with wedges or spacers and periodic level checks. | * UPSTREAM: Floor flatness * UPSTREAM: Layout pattern * UPSTREAM: Grout size * UPSTREAM: Tile flatness * Thinset volume * Thinset consistency * Thinset troweling * Thinset time since mix * Leveling system pressure * Location of leveling spacers * Tile setting pressure too low * Tile setting wiggle too little * Floor contamination | Lippage <1/32"
Install | Set | Set tile | Press and wiggle each tile into the mortar bed, maintaining consistent spacing with wedges or spacers and periodic level checks. | * For sheet-tile/mosaics especially pebble - remove pieces and place indiviaully * Back butter application | Thinset coverage 95% in wet zones, 80% in dry zones
Install | Set | Set tile | Press and wiggle each tile into the mortar bed, maintaining consistent spacing with wedges or spacers and periodic level checks. | * For sheet-tile/mosaics especially pebble - remove pieces and place indiviaully * Back butter application * Leveling system tightness | Grout line size per spec (+/- <1/64")
Install | Set | Set tile | Press and wiggle each tile into the mortar bed, maintaining consistent spacing with wedges or spacers and periodic level checks. | * For sheet-tile/mosaics especially pebble - remove pieces and place indiviaully * Back butter application * Leveling system tightness | Grout line size per spec (+/- <1/64")
Install | Set | Set tile | Press and wiggle each tile into the mortar bed, maintaining consistent spacing with wedges or spacers and periodic level checks. | * For sheet-tile/mosaics especially pebble - remove pieces and place indiviaully * Back butter application | Layout per plan (+/- 1/4")
Install | Set | Set tile | Press and wiggle each tile into the mortar bed, maintaining consistent spacing with wedges or spacers and periodic level checks. | * For sheet-tile/mosaics especially pebble - remove pieces and place indiviaully * Back butter application | Grout nominal centerline must be straight
Install | Set | Set tile | Press and wiggle each tile into the mortar bed, maintaining consistent spacing with wedges or spacers and periodic level checks. | * Thinset volume near clips * Thinset volume | Thinset lower than 1/8" from tile suface
Install | Set | Set tile | Press and wiggle each tile into the mortar bed, maintaining consistent spacing with wedges or spacers and periodic level checks. | * For sheet-tile/mosaics especially pebble - remove pieces and place indiviaully * Back butter application | Thinset time from mix within mfg spec - 1hr max duration
Install | Set | Set tile | Press and wiggle each tile into the mortar bed, maintaining consistent spacing with wedges or spacers and periodic level checks. | * For sheet-tile/mosaics especially pebble - remove pieces and place indiviaully * Back butter application | No visible sheet lines
Install | Set | Verify tile coverage | Remove tile and check coverage according to plan, re-install | * Check-point adhserence | Coverage >80% in floor, 95% in bath
Install | Set | Correct layout | Inspect grout lines and make ongoing corrections to align layout | * Visual check * Layout plan | Grout line size per plan
Install | Set | Correct layout | Inspect grout lines and make ongoing corrections to align layout | * Visual check * Layout plan | Grout line size per plan
Install | Install tile trim and baseboard | Install tile trim and baseboard | Fit bullnose profiles or baseboards at tile edges for a clean termination and edge protection. | * For sheet-tile/mosaics especially pebble - remove pieces and place indiviaully * Back butter application | Lippage <1/32"
Install | Install tile trim and baseboard | Install tile trim and baseboard | Fit bullnose profiles or baseboards at tile edges for a clean termination and edge protection. | * For sheet-tile/mosaics especially pebble - remove pieces and place indiviaully * Back butter application | Thinset coverage 95% in wet zones, 80% in dry zones
Install | Install tile trim and baseboard | Install tile trim and baseboard | Fit bullnose profiles or baseboards at tile edges for a clean termination and edge protection. | * For sheet-tile/mosaics especially pebble - remove pieces and place indiviaully * Back butter application | Grout line size per spec (+/- <1/64")
Install | Install tile trim and baseboard | Install tile trim and baseboard | Fit bullnose profiles or baseboards at tile edges for a clean termination and edge protection. | * For sheet-tile/mosaics especially pebble - remove pieces and place indiviaully * Back butter application | Grout line size per spec (+/- <1/64")
Install | Install tile trim and baseboard | Install tile trim and baseboard | Fit bullnose profiles or baseboards at tile edges for a clean termination and edge protection. | * For sheet-tile/mosaics especially pebble - remove pieces and place indiviaully * Back butter application | Layout per plan (+/- 1/4")
Install | Install tile trim and baseboard | Install tile trim and baseboard | Fit bullnose profiles or baseboards at tile edges for a clean termination and edge protection. | * For sheet-tile/mosaics especially pebble - remove pieces and place indiviaully * Back butter application | Grout nominal centerline must be straight
Install | Install tile trim and baseboard | Install tile trim and baseboard | Fit bullnose profiles or baseboards at tile edges for a clean termination and edge protection. | * For sheet-tile/mosaics especially pebble - remove pieces and place indiviaully * Back butter application | Thinset time from mix within mfg spec - 1hr max duration
Install | Install tile trim and baseboard | Install tile trim and baseboard | Fit bullnose profiles or baseboards at tile edges for a clean termination and edge protection. | * For sheet-tile/mosaics especially pebble - remove pieces and place indiviaully * Back butter application | Seated to wall
Install | Set | Clean thinset from tile | Using sponge and toothbrush, clean thinset from tile tops and in grout lines | * Cleaning pressure * UPSTREAM: Excess grout volume * Tile leveling spacer qty | Thinset >1/8" from surface in grout line
Install | Set | Clean thinset from tile | Using sponge and toothbrush, clean thinset from tile tops and in grout lines | * Cleaning pressure * UPSTREAM: Excess grout volume * Tile leveling spacer qty | Thinset coverage removed from tile
Install | Pausing mid-project | Prepare stop point | Cut space for leveling spacers and remove loose thinset | * Thinset removal accuracy * Tile setting pressure | Thinset removed from flooring not covered by tile
Install | Pausing mid-project | Prepare stop point | Cut space for leveling spacers and remove loose thinset | * Thinset removal accuracy * Tile setting pressure | Leveling clip added where next layer will be
Install | Pausing mid-project | Prepare stop point | Cut space for leveling spacers and remove loose thinset | * Thinset removal accuracy * Tile setting pressure | Tile set tight to leveling clip
Finish | Cleaning | Clean tools | Remove thinset from tools | * Thinset waste location; water rinse duration * Thinset removal accuracy | Thinset completely removed from tools
Install | Thinset curing | Cure thinset | Permanently set thinset | * Wait time * Humidity * Ambient temp | Tile lippage <1/32"
Install | Thinset curing | Cure thinset | Permanently set thinset | * Wait time * Humidity * Ambient temp | Thinset 100% cured
Install | Leveling system removal | Remove leveling clips | Snap off and remove leveling clips from tile surface | * Strike force * Strike angle | Level clips 100% removed
Install | Leveling system removal | Remove leveling clips | Snap off and remove leveling clips from tile surface | * Strike force * Strike angle | Breaklines >1/8" below surface
Finish | Grout & caulk | Tile cleaning | Remove excess thinset from tile surface and grout lines | *UPSTREAM: Incomplete cleaning * Cleaning / scraping pressure | Thinset >1/8" from surface in grout line
Finish | Grout & caulk | Tile cleaning | Remove excess thinset from tile surface and grout lines | *UPSTREAM: Incomplete cleaning * Cleaning / scraping pressure | Thinset coverage removed from tile
Finish | Grout & caulk | Grout | Fill joints with grout using a rubber float, working diagonally across tiles to compact and wipe excess grout from edges. | * Time since mix completion * Grout float angle * Cleaning force * Grout line coverage | 100% coverage of grout lines
Finish | Grout & caulk | Grout | Fill joints with grout using a rubber float, working diagonally across tiles to compact and wipe excess grout from edges. | * Time since mix completion * Grout float angle * Cleaning force * Grout line coverage | No grout on tile
Finish | Grout & caulk | Grout | Fill joints with grout using a rubber float, working diagonally across tiles to compact and wipe excess grout from edges. | * Time since mix completion * Grout float angle * Cleaning force * Grout line coverage | Tooled radius in grout line
Finish | Grout & caulk | Grout | Fill joints with grout using a rubber float, working diagonally across tiles to compact and wipe excess grout from edges. | * Time since mix completion * Grout float angle * Cleaning force * Grout line coverage | No grout in change of planes (corners)
Finish | Grout & caulk | Grout | Fill joints with grout using a rubber float, working diagonally across tiles to compact and wipe excess grout from edges. | * Time since mix completion * Grout float angle * Cleaning force * Grout line coverage | Grout integrity
Finish | Cleaning | Clean tools | Remove thinset from tools | * Thinset waste location; water rinse duration * Thinset removal accuracy | Thinset completely removed from tools
Finish | Grout & caulk | Caulk | Seal perimeter and transition joints with a flexible, mildew-resistant caulk that matches grout color to accommodate movement. | * Grout tip size * Expelled volume * Tape / masking placement | Caulk 100% covered
Finish | Grout & caulk | Caulk | Seal perimeter and transition joints with a flexible, mildew-resistant caulk that matches grout color to accommodate movement. | * Grout tip size * Expelled volume * Tape / masking placement | Caulk shaped with no reversals, defects or tile coverage
Finish | Seal | Seal | Apply penetrating or topical sealer to grout (and natural stone) to protect against stains and moisture ingress. | * Tape placement * Sealant application volume * Sealant coverage | Sealant applied to 100% of grout
Finish | Seal | Seal | Apply penetrating or topical sealer to grout (and natural stone) to protect against stains and moisture ingress. | * Tape placement * Sealant application volume * Sealant coverage | No sealant applied to tile
Finish | Seal | Seal | Apply penetrating or topical sealer to grout (and natural stone) to protect against stains and moisture ingress. | * Tape placement * Sealant application volume * Sealant coverage | Sealant protected from water and contamination for mfg-spec'd duration, at least 2hr
Finish | Install wood trim and baseboard | Install wood trim and baseboard | Reattach or install new wood moldings, mitered at corners, and nail them to the wall studs clear of the tile field. | * Baseboard cut length * Baseboard miter angle * UPSTREAM: Wall flatness * UPSTREAM: tile floor flatness | Moldings nailed per pattern
Finish | Install wood trim and baseboard | Install wood trim and baseboard | Reattach or install new wood moldings, mitered at corners, and nail them to the wall studs clear of the tile field. | * Baseboard cut length * Baseboard miter angle * UPSTREAM: Wall flatness * UPSTREAM: tile floor flatness | Moldings tight to wall
Finish | Install wood trim and baseboard | Install wood trim and baseboard | Reattach or install new wood moldings, mitered at corners, and nail them to the wall studs clear of the tile field. | * Baseboard cut length * Baseboard miter angle * UPSTREAM: Wall flatness * UPSTREAM: tile floor flatness | No visible gaps to wall or in wood trim
Finish | Install wood trim and baseboard | Install wood trim and baseboard | Reattach or install new wood moldings, mitered at corners, and nail them to the wall studs clear of the tile field. | * Baseboard cut length * Baseboard miter angle * UPSTREAM: Wall flatness * UPSTREAM: tile floor flatness | No caulk applied to wood-plane
Finish | Install toilet | Install toilet | Install toilet on to new toilet floor | * Flange height relative to finished floor * Toilet type * Toilet lift method * Toilet install method * Wax/seal type * Bolt length * Bolt alignment * Lifting mechanism vs weight | Toilet bolts mounted tight
Finish | Install toilet | Install toilet | Install toilet on to new toilet floor | * Flange height relative to finished floor * Toilet type * Toilet lift method * Toilet install method * Wax/seal type * Bolt length * Bolt alignment * Lifting mechanism vs weight | Toilet bolts mounted tight
Finish | Install toilet | Install toilet | Install toilet on to new toilet floor | * Flange height relative to finished floor * Toilet type * Toilet lift method * Toilet install method * Wax/seal type * Bolt length * Bolt alignment * Lifting mechanism vs weight | Toilet flat
Finish | Install toilet | Install toilet | Install toilet on to new toilet floor | * Flange height relative to finished floor * Toilet type * Toilet lift method * Toilet install method * Wax/seal type * Bolt length * Bolt alignment * Lifting mechanism vs weight | Toilet gap <1/8"
Finish | Install toilet | Install toilet | Install toilet on to new toilet floor | * Flange height relative to finished floor * Toilet type * Toilet lift method * Toilet install method * Wax/seal type * Bolt length * Bolt alignment * Lifting mechanism vs weight | Toilet caulked to floor
Finish | Complete project | Document completion | Using app, take photos, complete workflows, and provide feedback | * Flange height relative to finished floor * Toilet type * Toilet lift method * Toilet install method * Wax/seal type * Bolt length * Bolt alignment * Lifting mechanism vs weight | Photos, workflow, feedback completed
Finish | Prep for pickup | Prep for pickup | Clean tools and add to packaging | * Checklist & packaging method | Tools cleaned per cleaning plan
Finish | Prep for pickup | Prep for pickup | Clean tools and add to packaging | * Checklist & packaging method | 100% of tools returned
Finish | Materials disposal | Store leftover materials | Maintain a small collection of materials for future reference and replacement | * Storage location * Storage packaging * Item volume | 5 full pieces stored safely - packaged in bubblewrap
Finish | Materials disposal | Dispose of waste tile and leftover materials | Remove materials from property | * Waste compliance regulations * Disposal method | Materials removed from property
Finish | Materials disposal | Dispose of waste tile and leftover materials | Remove materials from property | * Waste compliance regulations * Disposal method | Nails not sticking out of wood/materials
Finish | Materials disposal | Dispose of waste tile and leftover materials | Remove materials from property | * Waste compliance regulations * Disposal method | Local waste compliance met
Finish | Post-install inspection | Inspect grout and tile | Check for cracks in grout and tile | * Inspection distance (spec: 36" from walls and 60" from floor) * Inspection coverage | 100% inspection completed under standard conditions